## Instructions
Instructions | Enter your team name as specified in the cell below. When doing cross-team acceptance testing, enter the name for the testing group. Fill-in the Test Plan worksheet with all the remaining User Stories in your Product Backlog. Since Product acceptance is from the perspective of the end-user, only add User Stories that pertain to the Owner or Buyer and do not include User Stories specifically for the REST API service (e.g. AS a developer...). As your user stories are refined, add the acceptance criteria for each user story. Use a separate worksheet to provide any specific test case data that the tester needs to use. As tests are performed in each sprint, indicate Pass/Fail. Note that there are separate columns for each sprint. The tester should add initials and a date in the comments column. If the test failed, the tester is required to add additional information about the failure. The status cell will color code based on the test results. The comments cell will color code when a test result exists but no information is entered. Save this test plan with a name formatted as "term-swen-261-sec-letter name", e.g. 2171-swen-261-10-a Speedy Racers.xslx. Submit this file per the instructions specified for the sprint submissions and cross-team testing.
Team Name | 2235-swen-261-06-2b-wizards
Testing Team Name | fill in when doing cross-team testing

## Test Plan
User Story | Acceptance Criterion | Sprint 2 | Tester initials; date; comments (required if test failed) | Sprint 3 | Tester initials; date; comments (required if test failed)
As a Buyer, I want to have a page which allows me to login, so that I can log in to my account and store my user data in the browser. | Given I input the correct credentials when I press the login button then I get redirected to the catalog. | Pass | JS 03/14/24
| Given I input the incorrect credentials when I press the login button then I get notified that either the username or password was incorrect via a tooltip. | Pass | JS 03/14/24
| Given I'm on the login page when I press the register button then I get redirected to the Register an Account page. | Pass | JS 03/14/24
As a Buyer, I want to have a webpage with allows me to sign up, so that I have an account which stores data such as my cart. | Given I input valid new credentials when I press the register account button, then it should create the account and redirect to the login page. | Pass | JS 03/14/24
| Given I input an already used username when I press the register account button, then I get notified that my username was already taken via a tooltip below the username field. | Pass | JS 03/14/24
| Given I input passwords that do not match when I press the register account button then I get notified that my passwords conflict via a tooltip below the password fields. | Pass | JS 03/14/24
As a Developer, I want to submit a request to create a new user, so that the account is available to serialize data. | Given I submit a new user object when no user with the given id exists then the system should create the user, save to file, and return a status code of 201. | Pass | JMB 3/14/24
| Given I submit a new user object when a user with the given id exists then the system should return a status code of 409 (Conflict) | Pass | JMB 3/14/24
As a Developer, I want to verify that an account signing in exists, so that their data can be deserialized and referenced from the front-end. | Given I submit the correct credentials when I sign in (POST /users/auth) then the system should return their User Data and 200 (OK) status code. | Pass | JMB 3/14/24
| Given I submit incorrect credentials when I sign in (POST /users/auth) then the system should return 401 (Unauthorized) status code. | Pass | JMB 3/14/24
As a Buyer, I want to have a part of the UI that allows me to log out, so that my account does not have to be permanently signed in to and other accounts can be used on the device. | Given I'm logged in when I press the logout button then I am logged out and sent to the login screen. | Pass | JS 03/14/24
| Given I'm logged out when I view where the logout button should be then I see the login button. | Pass | JS 03/14/24
As a Buyer, I want a page on the website which allows me to view the list of products, so that I may browse what is available. | Given I navigate to the products page when I view it then I can see a listing of all available products. | Pass | GBT Mar 14, 2024
| Given I start searching on the products page when product(s) are found then I can see a listing of all products that partially match the searched name. | Pass | GBT Mar 14, 2024
| Given I start searching on the products page when products are not found then I should see an error that no products were found. | Pass | GBT Mar 14, 2024
As an Owner, I want to have access to a separate admin page, so I can add another product to the catalog. | Given I am signed in as admin when I navigate to the admin page then I expect to have the option to add products. | Pass | ES 14 Mar 2024
| Given I am signed in as admin when I click add and supply a product name then I expect that product to be immediately added to the catalog. | Pass | ES 14 Mar 2024
As an Owner, I want to be able to update a single product from its detail page through the admin page, so that buyers can see the changes reflected in their view. | Given I am signed in as admin when I navigate to the admin page and click on a product then I expect to be able to view its details from a separate page. | Pass | ES 14 Mar 2024
| Given I am signed in as admin when I click save on a specific product's details from the admin page then I expect those changes to reflect in the catalog and see the admin view again. | Pass | ES 14 Mar 2024
As an Owner, I want to have access to delete product(s) from an admin page, so that Buyers can no longer buy the products from their view. | Given I am signed in as admin when I navigate to the admin page then I expect to be able to delete products via a button. | Pass | ES 14 Mar 2024
| Given I am signed in as admin when I click delete on a product from the admin page then I expect the product to be immediately removed from the inventory. | Pass | ES 14 Mar 2024
As a Developer, I want to have the system update users, so that data, such as their cart state, may be managed. | Given a user with the correct username exists when I PUT /users/ then the system should update the user with the provided username and return 200 (OK). | Pass | SB 14 Mar 2024
| Given a user with the correct username does not exists when I PUT /users/ then the system should return 404 (NOT FOUND). | Pass | SB 14 Mar 2024
As a Buyer, I want to see my chosen products in the cart, so that I can proceed to purchase products from the site. | Given I navigate to the cart page when the I have not added any products to my cart then the page will display not products. | Pass | SB 14 Mar 2024
| Given I navigate to the cart page when I have added at least one product to the cart then the page will display the products in my cart and their total price. | Pass | SB 14 Mar 2024
As a Buyer, I want to be able to add products to my cart, so that I can group the products I want to buy later. | Given I'm on the products page when a product is not already added to my cart then an add to cart button should appear by the product. | Pass | SB 14 Mar 2024
| Given I'm on the products page when I click the add to cart button on the active product then the product gets added to my cart. | Pass | SB 14 Mar 2024
As a Buyer, I want to be able to remove a product from my cart, so that I do not have to pay for it later from my shopping cart. | Given I'm on the products page when a product is already added to my cart then a remove from cart button should appear by the product. | Pass | SB 14 Mar 2024
| Given I'm on the cart page when I click a product's remove from cart button then the product gets removed from my cart. | Pass | SB 14 Mar 2024